## Slide 1: Reverse Trade Show / Reception/ NIGP Class Straw man Action Item List
Cindy Norton
nortonlj@santarosa.k12.fl.us
(850)983-5130
(850)324-9217

## Slide 2: – NIGP Continuing Education Class
Action | Who | When | Completed
Survey membership | Education Committee | Year prior to event | 
Budget | Treasurer | Board Established prior to Jan. | 
Reserve Conference Center Room & Tech Needs | Education Committee | As soon as venue and Date of Class & RTS is confirmed | 
Register for NIGP Seminar Host | Education Committee | After survey responses are reviewed; after date is confirmed | 
Define and Secure CE Class Content | Education Committee | ASAP | 
Announcement to Chapter | Education Committee | After confirmation of NIGP class host registration | 
2nd Announcement to Chapter | Education Committee | As necessary; before registration deadline | 
Material Reproduction | Education Committee | After registration deadline | 
Refreshment Order | Education Committee | After registration deadline | 
Welcome | Education Committee Chair | Before Class is to start | 

## Slide 3: RTS – Reception (reg. included in RTS package)
Action | Who | When | Est. Completion | Completed
Budget | Treasurer | Established prior to January |  | 
Reserve Venue/review contract | RTS Committee Chair | As soon as RTS venue is confirmed |  | 
Caterer for heavy hors d’oeuvres; cash bar | RTS Committee | Venue may have own caterer/bartender; if restaurant choose appetizers served |  | 
Info. on Website | Web Manager | As soon as RTS venue and date is confirmed |  | 
Announcement | RTS Committee | Included in RTS announcements |  | 
Name Badge | RTS Committee | Print after RTS registration deadline |  | 
Sponsorship Signage/ Signage for Venue | RTS Committee | After logos are due/early bird registration |  | 
Decorations/ Signage | RTS Committee | Order ASAP/ Setup 1 hour prior to start time |  | 
Name Badge Table | RTS Committee | Someone needs to greet guests and pass out name badge/lanyards. |  | 
Execute Reception | President | Welcome at event |  | 

## Slide 4: Reverse Trade Show
Action | Who | When | Est. Completion | Completed
Budget | Treasurer | Board established prior to January |  | 
Door Prize Collection from members | Marketing Chair | Announcements to members during year/bring to event | Before RTS day | 
Obtain Venue and sign contract | RTS Committee/ President | ASAP ; year in advance | 9 months prior to event | 
Create RTS website registration | Web Manager | After confirmation of date and venue | 9 months prior to event | 
Save the Date Card | Marketing Chair | After venue & date confirmed | 9 months prior to event | 
Event Flyer | Marketing Chair | After venue reserved | 9 months prior to event | 
Media Release | Marketing Chair | After Registration is open | ongoing | 
Chamber of Commerce Notice | Marketing Chair | After Registration is open | ongoing | 
Announcement to membership | RTS Committee Chair | After venue & Date is confirmed | 9 months prior to event & reminders as needed | 
Online Directory of membership | Marketing Chair | After logo is due/ Sponsorship advertisement is incl. | 2 weeks prior to event; send out to registered vendors | 
Meals/refreshments/ Caterer | RTS Committee | Review Venue or Caterer contract | 8 months prior | 

## Slide 5: Reverse Trade Show
Action | Who | When | Est. Completion | Completed
Name Badge Printing/ Assembly | RTS Committee | After registration closes |  | 
Name Badge Table | RTS Committee | Table at event with greeter |  | 
Event Signage printing | Marketing Committee | After Date & venue confirmed |  | 
Sponsorship Signage Printing | Marketing Committee | After registration closed |  | 
Schematics- table layout | RTS Committee | Venue contract signed |  | 
Signage Placement Plan | RTS Committee | Prior to event |  | 
Decorations | RTS Committee | Review needs 2 months prior |  | 
Welcome/ Announcements/ Sponsor Recognition | President/ V.P. | At Event |  | 
Awards – BOY / MOY presentation | Awards Chair | At Event |  | 
Event/Pictures/Video | Marketing Committee | During event & from membership after event |  | 
Clean up | RTS Committee | After event |  | 
Thank you Emails/Notes | Secretary/President | After event |  | 

## Slide 6: Reverse Trade Show
Action | Who | When | Est. Completion | Completed