## Attachment H - Instructions
Attachment H - Instructions
List of Schedules
Schedule | Title
Schedule A | Schedule A - Number of Full Time Equivalents (FTE) - Team CNSI Total
Schedule A - Number of Full Time Equivalents (FTE) - Prime Contractor
Schedule A - Number of Full Time Equivalents (FTE) - Subcontractor
Schedule B | Schedule B - Number of Hours - Team CNSI Total
Schedule B - Number of Hours - Prime Contractor Total
Schedule B - Number of Hours - Subcontractor Total
Instructions: Offerors must complete both Resource Allocation Schedules. These schedules serve as the representation of Offeror's plan for staffing the project by resource type. Offeror should include additional information as necessary to explain the Offeror's resource allocation. If the Offeror has one or more subcontractors, the Offeror must submit a Schedule A and Schedule B with a comprehensive total for all FTE and hours representing the effort of the prime contractor and all subcontractor work in total. In addition, a separate Schedule A and Schedule B for each contractor (prime contractor and subcontractor) must be submitted. All schedules must be completed in full at the time of submittal. The resource types listed in the schedule are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Add resource types necessary to successfully deliver the scope of work. Schedule A: This schedule details the number of full time equivalents the Offeror plans to allocate to the project by phase and by resource type. Schedule B: This schedule details the number of resource hours the Offeror plans to allocate to the project by phase and by resource type.
;

## Sch A Total FTEs by Phase
Schedule A - Number of Full Time Equivalents (FTE) - Team CNSI Total
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource FTE by Resource Type for all phases
Project Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 8.1346 | 8.6731
Contract Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 2.0337 | 2.5721
Testing Lead |  | 0.19231 | 0.125 | 0.067308 |  | 0.38462
Integration Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
Certification Lead |  |  | 0.05 | 0.026923 | 0.45192 | 0.52885
Business Operation Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 8.1346 | 8.6731
System Operations Manager |  |  |  |  | 8.1346 | 8.1346
Application Services Manager |  |  |  |  | 2.0337 | 2.0337
Infrastructure Manager |  |  |  |  | 2.0337 | 2.0337
Business Analyst | 0.61538 | 0.92308 | 0.5 | 0.26923 |  | 2.3077
Director Medicaid Services |  | 0.039543 | 0.028245 | 0.045192 | 0.22596 | 0.33894
Medicaid Services Supervisor |  | 0.13181 | 0.094151 | 0.15064 | 0.90385 | 1.2804
Site Visit Coordinator |  | 0.10545 | 0.075321 | 0.12051 | 1.8077 | 2.109
Operations Coordinator
Operations Analyst I |  | 0.015817 | 0.011298 | 0.018077 | 0.27115 | 0.31635
Customer Service Representative |  | 0.25308 | 0.18077 | 0.28923 | 4.3385 | 5.0615
Enrollment Representative |  | 0.11863 | 0.084736 | 0.13558 | 2.0337 | 2.3726
Education Representative |  | 0.052724 | 0.03766 | 0.060256 | 0.45192 | 0.60256
Training Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 | 2.0337 | 2.5721
Tester |  | 0.76923 | 0.5 | 0.26923 | 12.2019 | 13.7404
Project Scheduler | 0.076923 | 0.11538 | 0.05 | 0.026923 |  | 0.26923
Project Controls | 0.076923 | 0.11538 | 0.05 | 0.026923 | 2.0337 | 2.3029
Business Architect | 0.30769 | 0.46154 | 0.25 | 0.13462 |  | 1.1538
Technical Architect | 0.30769 | 0.46154 | 0.25 | 0.13462 |  | 1.1538
Technical Architect (PCS) | 0.076923 | 0.11538 | 0.05 | 0.026923 |  | 0.26923
Technical Writer | 0.46154 | 0.69231 | 0.325 | 0.175 |  | 1.6538
Management | 0.19231 | 0.28846 | 0.1625 | 0.0875 |  | 0.73077
Development Manager | 0.15385 | 0.22692 | 0.1025 | 0.055192 | 0.81346 | 1.3519
Technical Lead | 0.46154 | 0.69231 | 0.35 | 0.18846 | 4.0673 | 5.7596
Java Developer |  | 0.62125 | 0.38428 | 0.20692 | 15.5769 | 16.7894
Pl/SQL Developer |  | 0.62125 | 0.38428 | 0.20692 |  | 1.2124
EDI Lead | 0.15385 | 0.23077 | 0.15 | 0.080769 |  | 0.61538
EDI Developer |  | 0.39048 | 0.28428 | 0.15307 | 13.5433 | 14.3711
Siebel Developer |  | 0.4674 | 0.23428 | 0.12615 | 9.476 | 10.3038
IVR Developer |  | 0.4674 | 0.23428 | 0.12615 | 9.476 | 10.3038
DBA - Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 | 0.81346 | 0.86731
CM-Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 | 0.81346 | 0.86731
DS-Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
SysAdmin- Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
Database Administrator | 0.11538 | 0.17308 | 0.075 | 0.040385 | 2.8471 | 3.251
Configuration Specialist | 0.11538 | 0.42308 | 0.225 | 0.12115 | 2.0337 | 2.9183
Sys Admin | 0.076923 | 0.11538 | 0.05 | 0.026923 | 2.0337 | 2.3029
Ops Support Analyst |  |  |  |  | 2.0337 | 2.0337
NOC Engineer |  |  |  |  | 4.0673 | 4.0673
Security Engineer | 0.038462 | 0.023077 | 0.025 | 0.013462 | 0.81346 | 0.91346
COGNOS Administrator | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
Reports Developer | 0.53606 | 0.58278 | 0.28428 | 0.15307 | 7.4423 | 8.9985
DataStage (ETL) Administrator |  | 0.046154 |  | 0 |  | 0.046154
Conversion Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
Conversion Developer | 0.57452 | 0.4674 | 0.23428 | 0.12615 |  | 1.4023
Data Modeler | 0.015385 | 0.10769 | 0.0675 | 0.036346 |  | 0.22692
Interface Lead | 0.023077 | 0.034615 | 0.015 | 0.0080769 |  | 0.080769
Interface Developer | 0.65144 | 0.58278 | 0.28428 | 0.15307 | 7.4423 | 9.1139
Quality Assurance | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
SOA Lead | 0.038462 | 0.17308 | 0.15 | 0.080769 | 4.0673 | 4.5096
Average Resource FTE Per Phase | 0.18859 | 0.27144 | 0.1481 | 0.089392 | 4.2591 | 3.2235
Total Resources FTE Per Phase | 6.2236 | 13.0293 | 7.1089 | 4.3716 | 144.6192 | 175.3526
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.

## Sch A Prime FTEs by Phase
Schedule A - Number of Full Time Equivalents (FTE) - Prime Contractor
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource FTE by Resource Type for all phases
Project Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 8.1346 | 8.6731
Contract Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 2.0337 | 2.5721
Testing Lead |  | 0.19231 | 0.125 | 0.067308 |  | 0.38462
Integration Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
Certification Lead |  |  | 0.05 | 0.026923 | 0.45192 | 0.52885
Business Operation Manager | 0.15385 | 0.23077 | 0.1 | 0.053846 | 8.1346 | 8.6731
System Operations Manager |  |  |  |  | 8.1346 | 8.1346
Application Services Manager |  |  |  |  | 2.0337 | 2.0337
Infrastructure Manager |  |  |  |  | 2.0337 | 2.0337
Business Analyst | 0.61538 | 0.92308 | 0.5 | 0.26923 |  | 2.3077
Director Medicaid Services
Medicaid Services Supervisor
Site Visit Coordinator
Operations Coordinator
Operations Analyst I
Customer Service Representative
Enrollment Representative
Education Representative
Training Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 | 2.0337 | 2.5721
Tester |  | 0.76923 | 0.5 | 0.26923 | 12.2019 | 13.7404
Project Scheduler | 0.076923 | 0.11538 | 0.05 | 0.026923 |  | 0.26923
Project Controls | 0.076923 | 0.11538 | 0.05 | 0.026923 | 2.0337 | 2.3029
Business Architect | 0.30769 | 0.46154 | 0.25 | 0.13462 |  | 1.1538
Technical Architect | 0.30769 | 0.46154 | 0.25 | 0.13462 |  | 1.1538
Technical Architect (PCS) | 0.076923 | 0.11538 | 0.05 | 0.026923 |  | 0.26923
Technical Writer | 0.46154 | 0.69231 | 0.325 | 0.175 |  | 1.6538
Management | 0.19231 | 0.28846 | 0.1625 | 0.0875 |  | 0.73077
Development Manager | 0.15385 | 0.22692 | 0.1025 | 0.055192 | 0.81346 | 1.3519
Technical Lead | 0.46154 | 0.69231 | 0.35 | 0.18846 | 4.0673 | 5.7596
Java Developer |  | 0.62125 | 0.38428 | 0.20692 | 15.5769 | 16.7894
Pl/SQL Developer |  | 0.62125 | 0.38428 | 0.20692 |  | 1.2124
EDI Lead | 0.15385 | 0.23077 | 0.15 | 0.080769 |  | 0.61538
EDI Developer |  | 0.39048 | 0.28428 | 0.15307 | 13.5433 | 14.3711
Siebel Developer |  | 0.4674 | 0.23428 | 0.12615 | 9.476 | 10.3038
IVR Developer |  | 0.4674 | 0.23428 | 0.12615 | 9.476 | 10.3038
DBA - Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 | 0.81346 | 0.86731
CM-Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 | 0.81346 | 0.86731
DS-Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
SysAdmin- Mgmt | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
Database Administrator | 0.11538 | 0.17308 | 0.075 | 0.040385 | 2.8471 | 3.251
Configuration Specialist | 0.11538 | 0.42308 | 0.225 | 0.12115 | 2.0337 | 2.9183
Sys Admin | 0.076923 | 0.11538 | 0.05 | 0.026923 | 2.0337 | 2.3029
Ops Support Analyst |  |  |  |  | 2.0337 | 2.0337
NOC Engineer |  |  |  |  | 4.0673 | 4.0673
Security Engineer | 0.038462 | 0.023077 | 0.025 | 0.013462 | 0.81346 | 0.91346
COGNOS Administrator | 0.015385 | 0.023077 | 0.01 | 0.0053846 |  | 0.053846
Reports Developer | 0.53606 | 0.58278 | 0.28428 | 0.15307 | 7.4423 | 8.9985
DataStage (ETL) Administrator |  | 0.046154 |  |  |  | 0.046154
Conversion Lead | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
Conversion Developer | 0.57452 | 0.4674 | 0.23428 | 0.12615 |  | 1.4023
Data Modeler | 0.015385 | 0.10769 | 0.0675 | 0.036346 |  | 0.22692
Interface Lead | 0.023077 | 0.034615 | 0.015 | 0.0080769 |  | 0.080769
Interface Developer | 0.65144 | 0.58278 | 0.28428 | 0.15307 | 7.4423 | 9.1139
Quality Assurance | 0.15385 | 0.23077 | 0.1 | 0.053846 |  | 0.53846
SOA Lead | 0.038462 | 0.17308 | 0.15 | 0.080769 | 4.0673 | 4.5096
Average Resource FTE Per Phase | 0.18859 | 0.3003 | 0.1609 | 0.086783 | 5.02 | 3.4739
Total Resources FTE Per Phase | 6.2236 | 12.3123 | 6.5967 | 3.5521 | 134.5865 | 163.2712
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.

## Sch A Sub FTEs by Phase
Schedule A - Number of Full Time Equivalents (FTE) - Subcontractor
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource FTE by Resource Type for all phases
Project Manager
Contract Manager
Testing Lead
Integration Lead
Certification Lead
Business Operation Manager
System Operations Manager
Application Services Manager
Infrastructure Manager
Business Analyst
Director Medicaid Services |  | 0.039543 | 0.028245 | 0.045192 | 0.22596 | 0.33894
Medicaid Services Supervisor |  | 0.13181 | 0.094151 | 0.15064 | 0.90385 | 1.2804
Site Visit Coordinator |  | 0.10545 | 0.075321 | 0.12051 | 1.8077 | 2.109
Operations Coordinator
Operations Analyst I |  | 0.015817 | 0.011298 | 0.018077 | 0.27115 | 0.31635
Customer Service Representative |  | 0.25308 | 0.18077 | 0.28923 | 4.3385 | 5.0615
Enrollment Representative |  | 0.11863 | 0.084736 | 0.13558 | 2.0337 | 2.3726
Education Representative |  | 0.052724 | 0.03766 | 0.060256 | 0.45192 | 0.60256
Training Lead
Tester
Project Scheduler
Project Controls
Business Architect
Technical Architect
Technical Architect (PCS)
Technical Writer
Management
Development Manager
Technical Lead
Java Developer
Pl/SQL Developer
EDI Lead
EDI Developer
Siebel Developer
IVR Developer
DBA - Mgmt
CM-Mgmt
DS-Mgmt
SysAdmin- Mgmt
Database Administrator
Configuration Specialist
Sys Admin
Ops Support Analyst
NOC Engineer
Security Engineer
COGNOS Administrator
Reports Developer
DataStage (ETL) Administrator
Conversion Lead
Conversion Developer
Data Modeler
Interface Lead
Interface Developer
Quality Assurance
SOA Lead
Average Resource FTE Per Phase |  | 0.10244 | 0.073168 | 0.11707 | 1.4332 | 1.7259
Total Resources FTE Per Phase |  | 0.71705 | 0.51218 | 0.81949 | 10.0327 | 12.0814
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.

## Sch B Total Hrs by Phase
Schedule B - Number of Hours - Team CNSI Total
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource Hrs. by Resource Type for All Phases
Project Manager | 320 | 480 | 208 | 112 | 16920 | 18040
Contract Manager | 320 | 480 | 208 | 112 | 4230 | 5350
Testing Lead |  | 400 | 260 | 140 |  | 800
Integration Lead | 320 | 480 | 208 | 112 |  | 1120
Certification Lead |  |  | 104 | 56 | 940 | 1100
Business Operation Manager | 320 | 480 | 208 | 112 | 16920 | 18040
System Operations Manager |  |  |  |  | 16920 | 16920
Application Services Manager |  |  |  |  | 4230 | 4230
Infrastructure Manager |  |  |  |  | 4230 | 4230
Business Analyst | 1280 | 1920 | 1040 | 560 |  | 4800
Director Medicaid Services |  | 82.25 | 58.75 | 94 | 4230 | 4465
Medicaid Services Supervisor |  | 274.1667 | 195.8333 | 313.3333 | 16920 | 17703.3333
Site Visit Coordinator |  | 219.3333 | 156.6667 | 250.6667 | 33840 | 34466.6667
Operations Coordinator
Operations Analyst I |  | 32.9 | 23.5 | 37.6 | 5076 | 5170
Customer Service Representative |  | 526.4 | 376 | 601.6 | 81216 | 82720
Enrollment Representative |  | 246.75 | 176.25 | 282 | 38070 | 38775
Education Representative |  | 109.6667 | 78.3333 | 125.3333 | 8460 | 8773.3333
Training Lead | 320 | 480 | 208 | 112 | 4230 | 5350
Tester |  | 1600 | 1040 | 560 | 25380 | 28580
Project Scheduler | 160 | 240 | 104 | 56 |  | 560
Project Controls | 160 | 240 | 104 | 56 | 4230 | 4790
Business Architect | 640 | 960 | 520 | 280 |  | 2400
Technical Architect | 640 | 960 | 520 | 280 |  | 2400
Technical Architect (PCS) | 160 | 240 | 104 | 56 |  | 560
Technical Writer | 960 | 1440 | 676 | 364 |  | 3440
Management | 400 | 600 | 338 | 182 |  | 1520
Development Manager | 320 | 472 | 213.2 | 114.8 | 1692 | 2812
Technical Lead | 960 | 1440 | 728 | 392 | 8460 | 11980
Java Developer |  | 1292.19 | 799.3 | 430.39 | 32400 | 34921.88
Pl/SQL Developer |  | 1292.19 | 799.3 | 430.39 |  | 2521.88
EDI Lead | 320 | 480 | 312 | 168 |  | 1280
EDI Developer |  | 812.19 | 591.3 | 318.39 | 28170 | 29891.88
Siebel Developer |  | 972.19 | 487.3 | 262.39 | 19710 | 21431.88
IVR Developer |  | 972.19 | 487.3 | 262.39 | 19710 | 21431.88
DBA - Mgmt | 32 | 48 | 20.8 | 11.2 | 1692 | 1804
CM-Mgmt | 32 | 48 | 20.8 | 11.2 | 1692 | 1804
DS-Mgmt | 32 | 48 | 20.8 | 11.2 |  | 112
SysAdmin- Mgmt | 32 | 48 | 20.8 | 11.2 |  | 112
Database Administrator | 240 | 360 | 156 | 84 | 5922 | 6762
Configuration Specialist | 240 | 880 | 468 | 252 | 4230 | 6070
Sys Admin | 160 | 240 | 104 | 56 | 4230 | 4790
Ops Support Analyst |  |  |  |  | 4230 | 4230
NOC Engineer |  |  |  |  | 8460 | 8460
Security Engineer | 80 | 48 | 52 | 28 | 1692 | 1900
COGNOS Administrator | 32 | 48 | 20.8 | 11.2 |  | 112
Reports Developer | 1115 | 1212.19 | 591.3 | 318.39 | 15480 | 18716.88
DataStage (ETL) Administrator |  | 96 |  |  |  | 96
Conversion Lead | 320 | 480 | 208 | 112 |  | 1120
Conversion Developer | 1195 | 972.19 | 487.3 | 262.39 |  | 2916.88
Data Modeler | 32 | 224 | 140.4 | 75.6 |  | 472
Interface Lead | 48 | 72 | 31.2 | 16.8 |  | 168
Interface Developer | 1355 | 1212.19 | 591.3 | 318.39 | 15480 | 18956.88
Quality Assurance | 320 | 480 | 208 | 112 |  | 1120
SOA Lead | 80 | 360 | 312 | 168 | 8460 | 9380
Total Resource Hrs. Per Phase | 12945 | 27100.9867 | 14786.5333 | 9092.8533 | 467752 | 531677.3733
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.

## Sch B Prime Total Hrs by Phase
Schedule B - Number of Hours - Prime Contractor Total
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource Hrs. by Resource Type for All Phases
Project Manager | 320 | 480 | 208 | 112 | 16920 | 18040
Contract Manager | 320 | 480 | 208 | 112 | 4230 | 5350
Testing Lead |  | 400 | 260 | 140 |  | 800
Integration Lead | 320 | 480 | 208 | 112 |  | 1120
Certification Lead |  |  | 104 | 56 | 940 | 1100
Business Operation Manager | 320 | 480 | 208 | 112 | 16920 | 18040
System Operations Manager |  |  |  |  | 16920 | 16920
Application Services Manager |  |  |  |  | 4230 | 4230
Infrastructure Manager |  |  |  |  | 4230 | 4230
Business Analyst | 1280 | 1920 | 1040 | 560 |  | 4800
Director Medicaid Services
Medicaid Services Supervisor
Site Visit Coordinator
Operations Coordinator
Operations Analyst I
Customer Service Representative
Enrollment Representative
Education Representative
Training Lead | 320 | 480 | 208 | 112 | 4230 | 5350
Tester |  | 1600 | 1040 | 560 | 25380 | 28580
Project Scheduler | 160 | 240 | 104 | 56 |  | 560
Project Controls | 160 | 240 | 104 | 56 | 4230 | 4790
Business Architect | 640 | 960 | 520 | 280 |  | 2400
Technical Architect | 640 | 960 | 520 | 280 |  | 2400
Technical Architect (PCS) | 160 | 240 | 104 | 56 |  | 560
Technical Writer | 960 | 1440 | 676 | 364 |  | 3440
Management | 400 | 600 | 338 | 182 |  | 1520
Development Manager | 320 | 472 | 213.2 | 114.8 | 1692 | 2812
Technical Lead | 960 | 1440 | 728 | 392 | 8460 | 11980
Java Developer |  | 1292.19 | 799.3 | 430.39 | 32400 | 34921.88
Pl/SQL Developer |  | 1292.19 | 799.3 | 430.39 |  | 2521.88
EDI Lead | 320 | 480 | 312 | 168 |  | 1280
EDI Developer |  | 812.19 | 591.3 | 318.39 | 28170 | 29891.88
Siebel Developer |  | 972.19 | 487.3 | 262.39 | 19710 | 21431.88
IVR Developer |  | 972.19 | 487.3 | 262.39 | 19710 | 21431.88
DBA - Mgmt | 32 | 48 | 20.8 | 11.2 | 1692 | 1804
CM-Mgmt | 32 | 48 | 20.8 | 11.2 | 1692 | 1804
DS-Mgmt | 32 | 48 | 20.8 | 11.2 |  | 112
SysAdmin- Mgmt | 32 | 48 | 20.8 | 11.2 |  | 112
Database Administrator | 240 | 360 | 156 | 84 | 5922 | 6762
Configuration Specialist | 240 | 880 | 468 | 252 | 4230 | 6070
Sys Admin | 160 | 240 | 104 | 56 | 4230 | 4790
Ops Support Analyst |  |  |  |  | 4230 | 4230
NOC Engineer |  |  |  |  | 8460 | 8460
Security Engineer | 80 | 48 | 52 | 28 | 1692 | 1900
COGNOS Administrator | 32 | 48 | 20.8 | 11.2 |  | 112
Reports Developer | 1115 | 1212.19 | 591.3 | 318.39 | 15480 | 18716.88
DataStage (ETL) Administrator |  | 96 |  |  |  | 96
Conversion Lead | 320 | 480 | 208 | 112 |  | 1120
Conversion Developer | 1195 | 972.19 | 487.3 | 262.39 |  | 2916.88
Data Modeler | 32 | 224 | 140.4 | 75.6 |  | 472
Interface Lead | 48 | 72 | 31.2 | 16.8 |  | 168
Interface Developer | 1355 | 1212.19 | 591.3 | 318.39 | 15480 | 18956.88
Quality Assurance | 320 | 480 | 208 | 112 |  | 1120
SOA Lead | 80 | 360 | 312 | 168 | 8460 | 9380
Total Resource Hrs. Per Phase | 12945 | 25609.52 | 13721.2 | 7388.32 | 279940 | 339604.04
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.

## Sch B Sub Total Hrs by Phase
Schedule B - Number of Hours - Subcontractor Total
Resource Type | Phase
| Initiation / Requirements | Design, Build, Config | Testing | Deployment / Implementation / Certification | Operations | Total Resource Hrs. by Resource Type for All Phases
Project Manager
Contract Manager
Testing Lead
Integration Lead
Certification Lead
Business Operation Manager
System Operations Manager
Application Services Manager
Infrastructure Manager
Business Analyst
Director Medicaid Services |  | 82.25 | 58.75 | 94 | 4230 | 4465
Medicaid Services Supervisor |  | 274.1667 | 195.8333 | 313.3333 | 16920 | 17703.3333
Site Visit Coordinator |  | 219.3333 | 156.6667 | 250.6667 | 33840 | 34466.6667
Operations Coordinator
Operations Analyst I |  | 32.9 | 23.5 | 37.6 | 5076 | 5170
Customer Service Representative |  | 526.4 | 376 | 601.6 | 81216 | 82720
Enrollment Representative |  | 246.75 | 176.25 | 282 | 38070 | 38775
Education Representative |  | 109.6667 | 78.3333 | 125.3333 | 8460 | 8773.3333
Training Lead
Tester
Project Scheduler
Project Controls
Business Architect
Technical Architect
Technical Architect (PCS)
Technical Writer
Management
Development Manager
Technical Lead
Java Developer
Pl/SQL Developer
EDI Lead
EDI Developer
Siebel Developer
IVR Developer
DBA - Mgmt
CM-Mgmt
DS-Mgmt
SysAdmin- Mgmt
Database Administrator
Configuration Specialist
Sys Admin
Ops Support Analyst
NOC Engineer
Security Engineer
COGNOS Administrator
Reports Developer
DataStage (ETL) Administrator
Conversion Lead
Conversion Developer
Data Modeler
Interface Lead
Interface Developer
Quality Assurance
SOA Lead
Total Resource Hrs. Per Phase |  | 1491.4667 | 1065.3333 | 1704.5333 | 187812 | 192073.3333
The resource types listed are not exhaustive, nor should the Contractor assume that DPHHS is requesting resources from each category. Use any resource type listed above and/or add resource types necessary to successfully deliver the scope of work. Senior (Sr.) Positions are defined by a combination of education and experience and shall have a four year degree in a related field, and at least five (5) years of experience. In lieu of a four year degree, seven (7) years of experience is expected. All other positions must have a minimum of four (4) years of related experience. Please map your resource positions based on years of experience and educational requirements to the following generally named resource positions.