Implementation and Acceptance Requirements_ Base Requirements

Implementation and Acceptance Requirements - Describe in detail how your company will meet all the requirements identified in Attachment F, Implementation and Acceptance Section, IA01-IA07. Your response should include the requirement number identified in the attachment, followed by your detailed response. You must provide a response to all requirements identified in Attachment F, Implementation and Acceptance Section.

IA01

The Supplier shall follow the following process for deploying each proposed services and solution(s): 
a. Submit an implementation letter to the agency confirming that the solution is ready for implementation. 
b. Receive the agency's approval of the implementation letter, accepting the Supplier's confirmation. 
c. Deploy the services and solutions according to the approved Implementation Plan. 
d. Provide confirmation that the services and solutions have been deployed to production and the Supplier has completed within a timeframe as determined by the agency of operations without significant operational issues defined as no critical or high defects. 
e. Receive the agency's acceptance of the services and solutions implementation.

ANSWER: Benefit Recovery has successfully implemented projects for government agencies from federal clients to local or state clients. Each client has an implementation process that they want to follow. Benefit Recovery will submit its Project Implementation Plan to the State for review. Benefit Recovery encourages the State to review the plan and provide feedback to determine what accommodations to the plan are necessary that the State would like added within the scope of the project.

At the project kickoff meeting, Benefit Recovery provides the State with the Implementation Plan that clearly defines Benefit Recovery’s understanding of the scope of the project. The Implementation Plan should be reviewed by the State and feedback returned to Benefit Recovery within 10 business days. Maintaining a timeline of 10 business days is important to ensure there are no delays in the project for Benefit Recovery or the State. The approval of the Implementation Plan as modified, provides Benefit Recovery the authority to move forward as planned to ensure the project is completed in a timely and efficient manner.

Based on project requirements of the State, Benefit Recovery begins to install and configure software and hardware in the Benefit Recovery data center or in the State provided enclave once approvals are received.

The Implementation Plan provides all details related to:

- Hardware requirements

- Software requirements

- Firewall required tasks

- Server configurations

- Access control requirements based on job roles

Upon project completion, the State is notified through an implementation letter indicating that the solution has been configured according to the project requirements and that it is ready for implementation. After review, the State will provide approval of the implementation letter and acceptance of Benefit Recovery’s confirmation of implementation readiness. Benefit Recovery then deploys the solution in accordance with

the approved plan, providing the State confirmation that the project has been deployed and that there were no critical or high defects. The State will then provide confirmation that the deployment has been accepted.

If there is any deviation or issues that arise during implementation, the Benefit Recovery Project Management Team shall record these items into a Lessons Learned document for future reference and to share with the State.  The Lessons Learned process is part of the final Implementation Phase report that is delivered to the State after the deployment of the software and implementation tasks have been completed. Benefit Recovery does not consider the Implementation Phase complete until the State provides an approval of the submitted Implementation Report.

IA02

The Supplier shall develop an Implementation Plan in conjunction with the agency that describes activities, such as:
a. The rollout approach, including phased implementation, if necessary.
b. Overall integration approach
c. Approach to continuous integration of other modules or data from other data providing entities. 
d. Integration Testing, including coordination procedures with System Integrator, other modules, other stakeholders, and vendors.
e. Approach to continuous integration of other modules or data from other data providing entities. 
f. The proposed implementation schedule.
g. The rollback strategy.
h. Communication and Supplier support procedures.
i. Supplier and State roles and responsibilities.
j. Operational Readiness Checklist(s) that defines, in advance, the go/no-go decision, and all aspects of Supplier, solution, and State readiness.
k. All critical tasks that are required for cutover.
l. Post cutover monitoring.
m. The onsite and offsite user support provided by the Supplier and State during the initial solution implementation.
n. Solution acceptance procedures.
o. Tools and processes to ensure overall quality.
p. Describe post implementation production deployment process and activities.

ANSWER: Benefit Recovery has a standard Implementation Plan that is the baseline for starting service contracts or software-as-a-service contracts. The Implementation Plan is updated after a State review and discussions with the State to understand the definition and impact of requested changes. The Benefit Recovery Implementation Team follows the planned approach which is completed in phases as there are certain software configurations that cannot be conducted until all of the proper hardware and access controls to the environment have been completed.

If the project calls for ARMS PRO to be integrated with other enterprise system modules, the level of integration needs to be clearly defined and within scope. Benefit Recovery carries out all integration tasks in coordination with the State and other vendors based on the implementation schedule that is laid out in the Implementation Plan. When Benefit Recovery enters into a service contract, the plan indicates that ARMS PRO is to be run in a Benefit Recovery data center and not a State controlled data center. This presents some technical challenges as far as how communication requirements are to be carried out and what firewall permissions are implemented while maintaining proper security levels which are also

addressed in the Implementation Plan. With Software-As-A-Service contracts Benefit Recovery is open to running the ARMS PRO software in any environment that is required by the State in accordance with the license agreements that are established for use of the ARMS PRO software.

There are many sub-plans laid out within the Implementation Plan that define the software implementation procedures, rollback strategies for a failed installation, and an Operational Readiness Checklist which document the go, no go decisions.  These plans are distributed to all team members to ensure:

- All tasks are completed in the proper order

- Software release testing requirements are documented

- The approval authority who indicates successful completion against the checklist is identified.

The communication required during a software release is of utmost importance and all communication methods and expectations are delivered to all team members prior to beginning the release. The roles and responsibilities for all parties to include Benefit Recovery, the State, and any other vendors are disseminated to the State for approval and awareness.

Some members from different teams might need to be present on-site for implementation, but Benefit Recovery has found in prior implementations that it does not require staff to be on-site unless there are Benefit Recovery hardware items that need attention. Benefit Recovery’s prior TPL experience indicates that implementation and post implementation support are effectively provided from its remote location.

Any system integration with other modules that are determined to be part of the contract have test cases developed and added to the Testing Plan. To assure expected quality is met, the deployment of the software must be fully tested, and State approved to ensure contract and cutover requirements are met and all integrations are working properly.

Benefit Recovery’s Implementation Plan includes all tools, processes, acceptance procedures, and post implementation processes and activities to be conducted by Benefit Recovery staff and any other responsible parties. The post implementation review phase of the project includes an all stakeholder review of the implementation process and results providing both the State and Benefit Recovery feedback on how to improve future implementations.

IA03

The Supplier's environments (e.g., development, testing, training and production) shall be available and accessible twenty-four (24) hours a day, seven (7) days a week, with the exception of planned downtime due to system upgrades or routine maintenance. All planned downtime and maintenance outages shall be coordinated and approved by the agency at least five (5) business days in advance.

ANSWER: The Benefit Recovery team ensures that the ARMS PRO servers are online and available for staff to work 24 hours a day, 365 days a year. Scheduled downtime that lasts for a minimal number of hours for quarterly releases of the ARMS PRO software are communicated to and approved by the State at least 5 days in advance. These times shall be recorded to track the amount of time that ARMS PRO was actually down for the release.  Emergency changes and releases are performed after normal operating hours with the State’s prior approval which shall be requested at least 5 business days ahead of the release. An additional benefit of using the ARMS PRO application is that its business rules and workflow refinements are configurable and do not require downtime.

IA04

During the requirements validation sessions, the Supplier must demonstrate a solution and/or set of business services, before implementation, that will fully function after implementation based on

the requirements described in the RFP and publicly available policy documents, manuals, and fee schedules

ANSWER: Critical to the success of the project is the ability of Benefit Recovery to acknowledge, understand, and demonstrate the capability of ARMS PRO to perform the tasks which are aligned to customer business requirements. During the requirements validation sessions which precede implementation, our team demonstrates the current ability of ARMS PRO and its system features that meet the needs of the TPL service requirements as specified in the RFP. Our team is ready to present and provide access to a fully functional version of the ARMS PRO solution as it exists in a demonstration environment to ensure that the solution meets the needs of the core business practices.

IA05

The Supplier shall work with the agency to confirm the Supplier's understanding of the requirements and to clarify and/or elaborate requirements where necessary to achieve desired business outcomes.

ANSWER: During the requirements analysis and design phase, Benefit Recovery gathers input from the State to focus on developing the requirements of each of the system components, analyzes the requirements for clarity, and documents the defined requirements to move forward with design and configuration. Once business process requirements are defined, Benefit Recovery collaborates with the State to confirm the concepts meet the State requirements for TPL service.

IA06

The Supplier shall, during requirement validation, provide designated agency staff access to a fully functioning environment to become familiar with the solution and/or business services.

ANSWER: During the requirements validation phase, Benefit Recovery provides access to a fully functioning dedicated training platform. Recognizing the State requires flexible access, the validation database is created to mirror a production environment with at least an average of 99 percent operational readiness. The validation environment is available using a delivery method and platform that meets the requirements as specified in the RFP.

IA07

The Supplier shall utilize project control tools to formally track all requirements and related design, configuration, testing, and certification artifacts.  The Supplier's requirements management tool shall ensure approved changes to requirements are linked back the approved change request.

ANSWER: Benefit Recovery uses a requirements traceability matrix (RTM) to track the end-to-end life cycle of this project. The RTM provides traceability and ensures requirements are uniquely identified and tracked. The RTM contains the following artifacts:

- Business requirement number

- Associated functional requirements developed or modified that correlate to the business requirement and the functional requirement number

- Test case scenarios

- Specific test cases developed to test the requirements

- Test case status (e.g., failed or passed)

- Defects discovered during testing that may require additional work or further updates to requirements

- Approved Change Request (CR) number

Benefit Recovery has used this process successfully in other engagements where it has proven to be an instrumental tool in accomplishing the successful implementation and acceptance of the system and processes. The State can be assured that all requirements and artifacts are tracked and reported throughout the entire implementation phase of the project and that all changes are linked back to any approved change request.

Exhibit 1 - Sample Implementation Plan

| Task Name | Duration |
| --- | --- |
| Contract Award | 1 day |
| Project Implementation | 118.5 days |
| Kickoff Meeting | 1 day |
| Establish Points of Contact | 1 day |
| State Staff | 1 day |
| BR Staff | 1 day |
| Milestone: Transfer of Points of Contact Complete | 0 days |
| Define Roles and Responsibilities | 5 days |
| State Staff | 5 days |
| BR Staff | 5 days |
| Milestone: Defining of Roles and Responsibilities Complete | 0 days |
| Documentation | 54 days |
| BR Receives State TPL Program Letter of Authorization (LOA) | 5 days |
| BR Receives W9 from State | 5 days |
| BR Delivers Deliverable List for the Outgoing Contractor | 5 days |
| Delivery of BR Deliverable Plans | 5 days |
| Transition Plan | 5 days |
| Communication Plan | 5 days |
| Staffing Plan | 5 days |
| Testing Plan | 5 days |
| MS Project Work Plan | 5 days |
| Emergency Plan | 5 days |
| Disaster Recovery Plan | 5 days |
| Training Plan | 5 days |
| Turnover Plan | 5 days |
| Milestone: Submission BR Deliverables Complete | 0 days |
| Milestone: Documentation Implementation Tasks Complete | 0 days |
| Milestone: Kickoff Meeting | 0 days |
| Information Technology | 117.5 days |
| Current Issues with TPL Program | 7 days |
| BR Interfaces | 37.5 days |
| Establish SFTP Transfer Protocols | 1 day |
| Determine required project interfaces with State | 1 day |
| State delivers all interface access request documents | 1 day |
| BR completes all interface access requests | 2 days |
| BR submits all interface access requests | 1 day |
| BR develops interfaces based on State standards | 28.5 days |
| Test all required interfaces | 5 days |
| Milestone: BR Interfaces with State Complete | 0 days |
| Interface Data Files | 104.5 days |
| State Interface File Layouts | 86 days |
| BENDEX FILE | 10 days |
| COBC - ANSI837 FILE | 11.5 days |
| PAID CLAIMS FILE (FFS) | 10 days |
| BEHAVIORAL HEALTH ENCOUNTERS | 10 days |
| PHYSICAL HEALTH ENCOUNTERS | 10 days |
| NPI PROVIDER CROSSWALK | 10 days |
| FACILITY CODE FILE | 10 days |
| PROVIDER FILE | 10 days |
| PROCEDURE CODE FILE: | 10 days |
| DIAGNOSIS CODE (ICD9) FILE | 10 days |
| NDC FILE | 10 days |
| MMA FILE | 10 days |
| TPL COVERAGE FILE (RESOURCE) | 10 days |
| Milestone: State Interface File Layouts Complete | 0 days |
| Vendor Files (Layouts) | 10 days |
| MEDICARE A, B and Commercial Insurance VOID FILE | 10 days |
| PAID CLAIM RESOURCE FILE - COMMERCIAL | 10 days |
| Milestone: Vendor Files (Layouts) Complete | 0 days |
| State Interface Test File Delivery | 48 days |
| BENDEX FILE | 10 days |
| COBC - ANSI837 FILE | 10 days |
| PAID CLAIMS FILE (FFS) | 10 days |
| BEHAVIORAL HEALTH ENCOUNTERS | 10 days |
| PHYSICAL HEALTH ENCOUNTERS | 10 days |
| NPI PROVIDER CROSSWALK | 10 days |
| FACILITY CODE FILE | 10 days |
| ELIGIBILITY FILE ONE | 14.5 days |
| PROVIDER FILE | 10 days |
| PROCEDURE CODE FILE: | 10 days |
| DIAGNOSIS CODE (ICD9) FILE | 10 days |
| NDC FILE | 10 days |
| MMA FILE | 10 days |
| TPL COVERAGE FILE (RESOURCE) | 10 days |
| Milestone: State Interface Test File Delivery Complete | 0 days |
| Vendor Files to (Test Files) | 84 days |
| PAID CLAIM RESOURCE FILE - COMMERCIAL | 10 days |
| Milestone: Vendor Files to DPW Test Files Complete | 0 days |
| BR Reviews and Receives Updated Test Interface Files | 20 days |
| BR Approves Interface Files | 1 day |
| Milestone: State and BR Complete Interface File Testing | 0 days |
| BR Production Data Initiation | 75 days |
| Develop Loaders | 20 days |
| State Delivers Initial Production Data Files | 2 days |
| Load Production Data | 1 day |
| Review of Initial Production Data Load | 2 days |
| Milestone: BR Production Data Initiation Complete | 0 days |
| BR presents Provider Portal to State for Review | 1 day |
| Milestone: BR Information Technology Implementation Complete | 0 days |
| TPL Program Knowledge Transfer from State and Outgoing Contractor | 36 days |
| Touchpoint Meetings | 20 days |
| Initial Meeting with State and Outgoing Contractor | 1 day |
| BR Conducts On-Site Review and Assessment of Outgoing Contractor | 12 days |
| Due Diligence Review | 12 days |
| Operational Assessment | 12 days |
| Gap Analysis | 12 days |
| Inventory Statistics | 12 days |
| Productivity Rates | 12 days |
| Record Storage Information | 12 days |
| Special Project Activities | 12 days |
| Milestone: BR On-Site Review and Assessments Complete | 0 days |
| BR Delivers Finding Reports to State | 1 day |
| Due Diligence Review | 1 day |
| Operational Assessment | 1 day |
| Gap Analysis | 1 day |
| Inventory Statistics | 1 day |
| Productivity Rates | 1 day |
| Record Storage Information | 1 day |
| Special Project Activities | 1 day |
| Milestone: BR Delivery of Findings to State Complete | 0 days |
| State Systems, Data, and Outstanding Issues | 2 days |
| MMIS | 1 day |
| Beneficiary Data | 1 day |
| Provider Data | 1 day |
| Review of TRICARE | 1 day |
| Operations Overview | 1 day |
| Outstanding Issues | 1 day |
| Review of Medicare | 1 day |
| Operations Overview | 1 day |
| Outstanding Issues | 1 day |
| Review of Commercial Carriers | 1 day |
| Operations Overview | 1 day |
| Outstanding Issues | 1 day |
| Receive and Review Payer Overpayments (Credit Balances) | 1 day |
| Milestone: State Systems, Data, and Oustanding Issues Review Complete | 0 days |
| Daily Meetings (First 2 weeks) | 7 days |
| Milestone: State and Outgoing Contractor Touchpoint Meetings Complete | 0 days |
| Outgoing Contractor Data Requests | 21 days |
| Deliver Requested Data File Formats | 1 day |
| Provide all TPL claims billed over last 3 years | 10 days |
| Provide all TPL payments received over last 3 years | 10 days |
| Provide all TPL write-offs received over last 3 years | 10 days |
| Provide all TPL adjustments received over the last 3 years | 10 days |
| Provide all TPL denials received over last 3 years | 10 days |
| Provide all Provider Offset details for the last 3 years | 10 days |
| Provide all TPL claims billed with no response over last 3 years | 10 days |
| Provide all current payer billing rejections (electronic and paper) | 10 days |
| BR Conducts Review | 10 days |
| Milestone: Outgoing Contractor Data Request Delivery Complete | 0 days |
| Outgoing Contractor and State Reporting | 5 days |
| Provide Current AR Aging Report | 5 days |
| Milestone: Outgoing Contractor and Reporting State Delivery Complete | 0 days |
| Outgoing Contractor Payer Relations Transfer | 6 days |
| Delivery of all Payer Contact Information | 5 days |
| Outstanding Payer Issues Meeting | 1 day |
| Delivery of Payer Issues Documentation | 5 days |
| Milestone: Outgoing Contractor Payer Relations Knowledge Transfer Complete | 0 days |
| Milestone: State and Outgoing Contractor Knowledge Transfers Complete | 0 days |
| Documentation | 49 days |
| Transition Plan | 49 days |
| State Review and Approval | 10 days |
| Deliver Transitions Result Report | 1 day |
| State Review and Approval of Transitions Result Report | 5 days |
| Communication Plan | 10 days |
| State Review and Approval | 10 days |
| Staffing Plan | 10 days |
| State Review and Approval | 10 days |
| Testing Plan | 10 days |
| State Review and Approval | 10 days |
| MS Project Work Plan | 10 days |
| State Review and Approval | 10 days |
| Emergency Plan | 10 days |
| State Review and Approval | 10 days |
| Disaster Recovery Plan | 10 days |
| State Review and Approval | 10 days |
| Training Plan | 10 days |
| State Review and Approval | 10 days |
| Turnover Plan | 10 days |
| State Review and Approval | 10 days |
| Milestone: Documentation Reviews Complete | 0 days |
| BR Payer Relations Implementation | 63.5 days |
| Deliver to all Payers the new State TPL Program LOA | 30 days |
| Deliver to all Payers the W9 received from State | 30 days |
| Complete Data Use Agreements (For payers where no DUA present with BR) | 15 days |
| Payer Implementation Setup Tasks | 43.5 days |
| Payer sends SFTP or Webservice Protocols | 5 days |
| BR implements and test SFTP and Webservice Connectivity | 5 days |
| Payer uploads eligibility file to BR for State | 20 days |
| Milestone: Payer Implementation Setup Tasks Complete | 0 days |
| Milestone: BR Payer Relations Implementation Complete | 0 days |
| Milestone: Project Implementation Complete | 0 days |