## 1-500 Wearers
ID Name | Task Name | Duration/Days | Start | Finish | Preceeding Task | Resource Names
| ELECTRONIC MONITORING PROJECT UNTIL 1000 Smart Tags | 15 | 2023-05-14 | 2023-05-29
Preliminaries
1 | Contract signing | 1 | 2023-05-14 | 2023-05-15 |  | Buddi;Customer
2 | Constitution of policies | 1 | 2023-05-15 | 2023-05-16 | 1 | Buddi
3 | Signing of the act of initiation of the project | 1 | 2023-05-16 | 2023-05-17 | 2 | Buddi;Customer
Purchase orders
4 | Datacenter Principal provisioning | 1 | 2023-05-17 | 2023-05-18 | 3 | Buddi
5 | Datacenter Secondary provisioning | 1 | 2023-05-17 | 2023-05-18 | 3 | Buddi
6 | GPS device assembly including set up | 3 | 2023-05-18 | 2023-05-21 | 4 | Buddi
7 | IT tools for project personnel (laptops, cellphones or tablets) | 3 | 2023-05-18 | 2023-05-21 | 3 | Buddi
Detailed work plan
8 | Pre-Implementation meetings | 2 | 2023-05-16 | 2023-05-18 | 2 | Buddi;Customer
9 | Plan execution (Who/What/Where/When/How) | 1 | 2023-05-18 | 2023-05-19 | 8 | Buddi;Customer
10 | Define software configuration and report with authorities. | 1 | 2023-05-18 | 2023-05-19 | 8 | Buddi;Customer
11 | Define amount of units (clients) to swap and new installations | 1 | 2023-05-19 | 2023-05-20 | 9 | Buddi;Customer
12 | Confirm/adjust amount of GPS units to assembly, configure and ship | 1 | 2023-05-19 | 2023-05-20 | 9 | Buddi;Customer
13 | Development of Configurations | 5 | 2023-05-20 | 2023-05-25 | 10 | Buddi
14 | Training/User testing of Configured software. | 3 | 2023-05-26 | 2023-05-29 | 13 | Buddi,Customer
15 | Operations Accountability Matrix | 1 | 2023-05-20 | 2023-05-21 | 12 | Buddi;Customer
16 | Preparation of transition protocol (new installations or changes in technology) | 1 | 2023-05-21 | 2023-05-22 | 15 | Buddi;Customer
17 | Develop field service manuals (installation, uninstallation and maintenance), based on the requirements defined in previous activities. | 2 | 2023-05-20 | 2023-05-22 | 12 | Buddi
18 | Develop operational manuals for service monitoring and alarm escalation, based on requirements defined in previous activities. | 4 | 2023-05-20 | 2023-05-24 | 12 | Buddi
19 | Approval of operations manuals | 1 | 2023-05-24 | 2023-05-25 | 18 | Customer
20 | Develop training of final Users program and manuals based on protocols approved | 2 | 2023-05-24 | 2023-05-26 | 18 | Buddi
Data Center, Monitoring center and field services set up
21 | Setup and commissioning of monitoring software as per previous approval | 2 | 2023-05-19 | 2023-05-21 | 10 | Buddi
22 | Train monitoring center personnel based on approved protocols | 2 | 2023-05-26 | 2023-05-28 | 20 | Buddi
Reception and distribution of equipment based on identified workload
23 | GPS devices | 2 | 2023-05-21 | 2023-05-23 | 12 | Buddi
24 | IT tools | 2 | 2023-05-21 | 2023-05-23 | 7 | Buddi
Initial provisioning and testing (first units to callibrate processes)
25 | GPS devices | 1 | 2023-05-24 | 2023-05-25 | 23 | Buddi;Customer
26 | Update operation manuals | 2 | 2023-05-25 | 2023-05-27 | 19 | Buddi
27 | Approval of updated operations manuals | 2 | 2023-05-27 | 2023-05-29 | 19 | Customer
28 | Reinforce training for monitoring center and field personnel | 2 | 2023-05-28 | 2023-05-30 | 22 | Buddi
29 | Distribution of county usernames | 2 | 2023-05-26 | 2023-05-28 | 20 | Buddi
30 | Acceptance Tests Of Devices, Monitoring Center and Inventory | 2 | 2023-05-21 | 2023-05-23 | 21 | Customer
31 | Approval for the first installation | 1 | 2023-05-28 | 2023-05-29 | 22 | Customer
Start of Installing of Devices
32 | Go Live (2) Weeks | 5 | 2023-05-29 | 2023-06-03 | 31 | Buddi;Customer
Start of Monitoring Devices
33 | Device monitoring | 15 | 2023-05-29 | 2023-06-13 | 32 | Customer
End Of implementation project - begins project execution
Formulas:
Duration/Days = DAYS([Finish],[Start])
Start = [Finish, row above]
Start = +[Finish, row above]
Finish = +[Start]+[Duration/Days]

## 501-1000 Wearers
ID Name | Task Name | Duration/Days | Start | Finish | Preceeding Task | Resource Names
| ELECTRONIC MONITORING PROJECT UNTIL 1000 Smart Tags | 23 | 2023-05-06 | 2023-05-29
Preliminaries
1 | Contract signing | 1 | 2023-05-06 | 2023-05-07 |  | Buddi;Customer
2 | Constitution of policies | 4 | 2023-05-07 | 2023-05-11 | 2 | Buddi
3 | Signing of the act of initiation of the project | 1 | 2023-05-07 | 2023-05-08 | 2 | Buddi;Customer
Purchase orders
4 | Datacenter Principal provisioning | 6 | 2023-05-08 | 2023-05-14 | 3 | Buddi
5 | Datacenter Secondary provisioning | 6 | 2023-05-09 | 2023-05-15 |  | Buddi
6 | GPS device assembly including set up | 3 | 2023-05-08 | 2023-05-11 | 4 | Buddi
7 | IT tools for project personnel (laptops, cellphones or tablets) | 2 | 2023-05-08 | 2023-05-10 | 3 | Buddi
Detailed work plan
8 | Kickoff meetings | 3 | 2023-05-11 | 2023-05-14 | 2 | Buddi;Customer
9 | Plan execution | 1 | 2023-05-14 | 2023-05-15 | 8 | Buddi;Customer
10 | Define software configuration and report with authorities. | 2 | 2023-05-14 | 2023-05-16 | 8 | Buddi;Customer
11 | Define amount of units (clients) to swap and new installations | 2 | 2023-05-15 | 2023-05-17 | 9 | Buddi;Customer
12 | Confirm/adjust amount of GPS units to assembly, configure and ship | 2 | 2023-05-15 | 2023-05-17 | 9 | Buddi;Customer
13 | Development of Configurations | 5 | 2023-05-17 | 2023-05-22 | 10 | Buddi
14 | Training/User testing of Configured software. | 4 | 2023-05-23 | 2023-05-27 | 13 | Buddi,Customer
15 | Operations Accountability Matrix | 2 | 2023-05-17 | 2023-05-19 | 12 | Buddi;Customer
16 | Preparation of transition protocol (new installations or changes in technology) | 2 | 2023-05-19 | 2023-05-21 | 15 | Buddi;Customer
17 | Develop field service manuals (installation, uninstallation and maintenance), based on the requirements defined in previous activities. | 2 | 2023-05-17 | 2023-05-19 | 12 | Buddi
18 | Develop operational manuals for service monitoring and alarm escalation, based on requirements defined in previous activities. | 4 | 2023-05-17 | 2023-05-21 | 12 | Buddi
19 | Approval of operations manuals | 1 | 2023-05-21 | 2023-05-22 | 18 | Customer
20 | Develop training of final Users program and manuals based on protocols approved | 2 | 2023-05-21 | 2023-05-23 | 18 | Buddi
Data Center, Monitoring center and field services set up
21 | Setup and commissioning of monitoring software as per previous approval | 3 | 2023-05-14 | 2023-05-17 | 4 | Buddi
22 | Train monitoring center personnel based on approved protocols | 2 | 2023-05-23 | 2023-05-25 | 20 | Buddi
Reception and distribution of equipment based on identified workload
23 | GPS devices | 2 | 2023-05-11 | 2023-05-13 | 6 | Buddi
24 | IT tools | 2 | 2023-05-10 | 2023-05-12 | 7 | Buddi
Initial provisioning and testing (first units to callibrate processes)
25 | GPS devices | 2 | 2023-05-23 | 2023-05-25 | 20 | Buddi;Customer
26 | Update operation manuals | 1 | 2023-05-22 | 2023-05-23 | 19 | Buddi
27 | Approval of updated operations manuals | 1 | 2023-05-22 | 2023-05-23 | 19 | Customer
28 | Reinforce training for monitoring center and field personnel | 1 | 2023-05-25 | 2023-05-26 | 22 | Buddi
29 | Distribution of county usernames | 1 | 2023-05-23 | 2023-05-24 | 20 | Buddi
30 | Acceptance Tests Of Devices, Monitoring Center and Inventory | 1 | 2023-05-17 | 2023-05-18 | 21 | Customer
31 | Approval for the first installation | 1 | 2023-05-28 | 2023-05-29 | 22 | Customer
Start of Installing of Devices
32 | Go Live (2) Weeks | 14 | 2023-05-29 | 2023-06-12 | 31 | Buddi;Customer
Start of Monitoring Devices
33 | Device monitoring | 14 | 2023-05-29 | 2023-06-12 | 32 | Customer
End Of implementation project - begins project execution
Formulas:
Start = +[Finish, row above]
Start = +[Start, row above]+1
Finish = +[Start]+[Duration/Days]

## 1001-5000 Wearers
ID Name | Task Name | Duration/Days | Start | Finish | Preceeding Task | Responsible Party
| ELECTRONIC MONITORING PROJECT UNTIL 5000 Smart Tags | 36 | 2023-04-23 | 2023-05-29
Preliminaries
1 | Contract signing | 1 | 2023-04-23 | 2023-04-24 |  | Buddi;Customer
2 | Constitution of policies | 2 | 2023-04-24 | 2023-04-26 | 2 | Buddi
3 | Signing of the act of initiation of the project | 1 | 2023-04-24 | 2023-04-25 | 2 | Buddi;Customer
Purchase orders
4 | Datacenter Principal provisioning | 10 | 2023-04-25 | 2023-05-05 | 3 | Buddi
5 | Datacenter Secondary provisioning | 10 | 2023-04-28 | 2023-05-08 |  | Buddi
6 | GPS device assembly including set up | 10 | 2023-04-25 | 2023-05-05 | 4 | Buddi
7 | IT tools for project personnel (laptops, cellphones or tablets) | 2 | 2023-04-25 | 2023-04-27 | 3 | Buddi
Detailed work plan
8 | Kickoff meetings | 5 | 2023-04-27 | 2023-05-02 | 2 | Buddi;Customer
9 | Plan execution | 8 | 2023-05-02 | 2023-05-10 | 8 | Buddi;Customer
10 | Define software configuration and report with authorities. | 3 | 2023-05-02 | 2023-05-05 | 8 | Buddi;Customer
11 | Define amount of units (clients) to swap and new installations | 3 | 2023-05-10 | 2023-05-13 | 9 | Buddi;Customer
12 | Confirm/adjust amount of GPS units to assembly, configure and ship | 3 | 2023-05-10 | 2023-05-13 | 9 | Buddi;Customer
13 | Development of Configurations | 6 | 2023-05-02 | 2023-05-08 | 10 | Buddi
14 | Training/User testing of Configured software. | 5 | 2023-05-06 | 2023-05-11 | 13 | Buddi,Customer
15 | Operations Accountability Matrix | 4 | 2023-05-11 | 2023-05-15 | 12 | Buddi;Customer
16 | Preparation of transition protocol (new installations or changes in technology) | 3 | 2023-05-15 | 2023-05-18 | 15 | Buddi;Customer
17 | Develop field service manuals (installation, uninstallation and maintenance), based on the requirements defined in previous activities. | 4 | 2023-05-13 | 2023-05-17 | 12 | Buddi
18 | Develop operational manuals for service monitoring and alarm escalation, based on requirements defined in previous activities. | 4 | 2023-05-13 | 2023-05-17 | 12 | Buddi
19 | Approval of operations manuals | 2 | 2023-05-17 | 2023-05-19 | 18 | Customer
20 | Develop training of final Users program and manuals based on protocols approved | 2 | 2023-05-17 | 2023-05-19 | 18 | Buddi
Data Center, Monitoring center and field services set up
21 | Setup and commissioning of monitoring software as per previous approval | 6 | 2023-05-05 | 2023-05-11 | 4 | Buddi
22 | Train monitoring center personnel based on approved protocols | 3 | 2023-05-19 | 2023-05-22 | 20 | Buddi
Reception and distribution of equipment based on identified workload
23 | GPS devices | 2 | 2023-05-05 | 2023-05-07 | 6 | Buddi
24 | IT tools | 2 | 2023-04-27 | 2023-04-29 | 7 | Buddi
Initial provisioning and testing (first units to callibrate processes)
25 | GPS devices | 8 | 2023-05-19 | 2023-05-27 | 20 | Buddi;Customer
26 | Update operation manuals | 2 | 2023-05-19 | 2023-05-21 | 19 | Buddi
27 | Approval of updated operations manuals | 2 | 2023-05-19 | 2023-05-21 | 19 | Customer
28 | Reinforce training for monitoring center and field personnel | 3 | 2023-05-22 | 2023-05-25 | 22 | Buddi
29 | Distribution of county usernames | 3 | 2023-05-19 | 2023-05-22 | 20 | Buddi
30 | Acceptance Tests Of Devices, Monitoring Center and Inventory | 2 | 2023-05-11 | 2023-05-13 | 21 | Customer
31 | Approval for the first installation | 2 | 2023-05-27 | 2023-05-29 | 22 | Customer
Start of Installing of Devices
32 | Go Live (2) Weeks | 14 | 2023-05-29 | 2023-06-12 | 31 | Buddi;Customer
Start of Monitoring Devices
33 | Device monitoring | 14 | 2023-05-29 | 2023-06-12 | 31 | Customer
End Of implementation project - begins project execution
Formulas:
Start = +[Finish, row above]
Start = +[Start, row above]+3
Finish = +[Start]+[Duration/Days]

## Sheet1
| Demographin Informaiton Needed for Successful Transition |  | Customer User Profile Information Needed
1 | Wearer Name (Required) | 1 | Full Name
2 | Wearer ID– if applicable | 2 | Email
3 | Date of Birth - optional | 3 | Cell Phone - Mandatory for SMS Notificaitons and Mobile App Access
4 | General Demographic Data (size, weight, hair/eye color) - optional | 4 | Permission Level Access (i.e. Standard/Manager/Administrative)
5 | Home Address (Required) | 5 | Wearer Group Access
6 | Work Address or any other address necessary can be optional
7 | Offender Picture - optional
8 | Zones needed for restrictions – as applicable
9 | Curfew schedules – as applicable
10 | Risk Level
11 | Supervising officer of the wearer – mandatory for closed loop alert